## Sheet1
Task | Start Date | day to Complete
Information Gathering | 2021-06-19 | 7
Planning | 2021-07-04 | 14
Designing | 2021-07-18 | 14
Content and Writing Assembly | 2021-07-24 | 14
Coding | 2021-08-15 | 21
Testing, and review launch | 2021-09-05 | 21
44366